## Sheet1
Task Name | Feb | Mar |  |  |  | Apr |  |  | May
| Week1 | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Week1
1- Hosting domain (Picking Cloud platform). | Abbas, Omar, Ali
2- Create a website (create pages). |  |  | Abbas, Omar
3- Design images. |  |  | Ali
3- Developing the website (Coding) |  |  | Abbas, Omar, Ali
4- APIs implementation (calling APIs). |  |  |  | Omar
5- Testing web (9 Major tests). |  |  |  |  | Ali, Omar, Ali
Functionality Testing |  |  |  |  | Ali
Test Forms |  |  |  |  | Abbas
Test HTML and CSS |  |  |  |  | Abbas
Usability testing |  |  |  |  | Ali
Interface Testing |  |  |  |  | Omar
Database Testing |  |  |  |  | Omar
Browser Compatibility Test. |  |  |  |  | Abbas
Performance Testing: |  |  |  |  | Abbas, Ali
Security testing (SSL & Payments): | [6 empty] | Omar, Ali, Abbas
6- Publishing the website. (Finalize) | [8 empty] | Ali, Omar, Ali